Statement of fund for Capacity Building of PRIs & Municipalities for 2006-07 under BRGF for eleven districts of West Bengal.

| Code No. | Activity Details | Unit Cost (in Rs. lakh) | 2006-07 |  | % of Total | To be implemented by | Strategy of Implementation |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Ph | Fin |  |  |  |
| 001 | Survey on backwardness and development of baseline in all districts | 2.00 (Lump sum) per district | 11 | 22.00 | 2.10 | State Level | To be done through a team of experts to be deployed and monitored by the SRD Cell |
| 002 | IT Support to selected Panchayats & Municipalities for acquiring one computer and peripherals, including equipment to access internet connectivity and handholding support [@20 sets for Uttar Dinajpur & Dakshin Dinajpur and @ 30 sets for other districts] | 0.60 per unit of Panchayat & Municipality | 310 | 186.00 | 17.71 | District level | To be centrally procured by Zilla Parishads and the respective Municipalities. This activity will continue until each local body gets this support. |
| 003 | Support to SIPRD & Institute of Local Government & Urban Studies (ILGUS) for training of functionaries of PSs, ZPs & Municipalities | 5 (Lump Sum) | 1 | 5.00 | 0.48 | State Level | This support would be provided to SIPRD/ILGUS in terms of Activity Plans to be approved by Panchayats & Rural Development Department. |
| 004 | Support to ETCs for training of GP employees on issues related to institutional strengthening of GPs | 3.00 (Lump sum) per ETC | 4 | 12.00 | 1.14 | State Level | This support would be provided to ETCs in terms of Activity Plans to be approved by Panchayats & Rural Development Department. |
| 005 | Support to big districts, viz. South 24 Parganas, Murshidabad, Paschim Medinipur, Purba Medinipur for training of key GP & PS functionaries | 24.00 (Lump sum per district) | 4 | 96.00 | 9.14 | District Level | This support would be provided to DPRDOs for training under guidance of Commissioner of P&RD in terms of Activity Plans to be approved by Panchayats & Rural Development Department. |
| 006 | Support of medium size districts, viz. Malda, Purulia, Birbhum, Jalpaiguri & Bankura for training of GP & PS functionaries | 18.00 (Lump sum per district) | 5 | 90.00 | 8.57 | District Level | - do - |
| 007 | Support to small districts, viz. Uttar Dinajpur & Dakshin Dinajpur for training of GP & PS functionaries | 10.00 (Lump sum per district) | 2 | 20.00 | 1.90 | District Level | - do - |
| 008 | Establishment and maintenance of Helpline at the state level to start with | 1.00 (Lump sum) |  | 1.00 | 0.10 | State Level | To be implemented by the SRD Cell. This would be extended to the districts gradually. |
| 009 | Procurement of Training materials through SIPRD/ILGUS for all districts | Lump sum |  | 20.00 | 1.90 | State Level | This support would be provided to SIPRD in terms of the approved Action Plan. |

Ph= Physical;  Fin = Financial

Contd……P/2.

-::(2)::-

| Code No. | Activity Details | Unit Cost (in Rs. lakh) | 2006-07 |  | % of Total | To be implemented by | Strategy of Implementation |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Ph | ### Fin |  |  |  |
| 010 | Assistance to Panchayats and Municipalities (2061 Gram Panchayats, 215 Panchayat Samities, 11 Zilla Parishads and 51 Municipalities) for plan preparation and assistance to District Planning Committee for consolidation of plans. | 0.10 to 1901 GPs;0. 70 to 160 GPs;0. 15 to 215 PSs & 51 Municipalities; And 2.0 to 11 ZPs | All | 364.00 | 34.67 | All PRIs & all Municipalities | This support would be provided to all PRIs (GPs, PSs and ZPs) and all Municipalities for preparation and consolidation of plans under guidance of the SRD Cell in convergence with support from SRD |
| 011 | Support for setting up and maintenance of satellite based Receive Only Terminals (ROTs) to connect selected Gram Panchayats & Municipalities [in remotest areas in the first year]. | 0.30 per Gram Panchayat & Municipality | 125 | 37.50 | 3.57 | State Level | To be implemented by the SRD Cell, This would be extended to all the GPs and Municipalities gradually in convergence with support from SRD. |
| 012 | Support for setting up Training-cum-Resource Institution in each Zilla Parishad. | 12.00 per Unit | 11 | 132.00 | 12.57 | District Level | To be implemented by the SRD Cell, This would be extended gradually in convergence with support from SRD. |
| 013 | Support for strengthening training infrastructure of SIPRD | 10.00 (Lump sum) | 1 | 10.00 | 0.95 | State Level | This support would be provided to SIPRD in terms of the approved Action Plan. |
| 014 | Support for strengthening training infrastructure in 4 ETCs & one Regional Training Centre. | 5.00 (Lump sum) per ETC | 5 | 25.00 | 2.38 | State Level | This support would be provided to the ETCs in terms of the approved Action Plan. |
| 015 | Technical assistance (utilizing the scope of outsourcing) for planning & implementation, accessing the service of Resource Persons in implementation of BRGF including setting up and maintenance of MIS including monitoring, evaluation & documentation. | Lump sum |  | 29.50 | 2.81 | State Level | To be implemented by the SRD Cell in consultation with all concerned wings of Panchayats & Rural Development Department & Municipal Affairs Department. |
| # Total ::- |  |  |  | 1050.00 | 100.00 |  |  |

Ph= Physical;  Fin = Financial

(D. Ghosh)

Joint Secretary to the

Government of West Bengal

## File;\C2\dhurjati\Statement of fund for Capacity Building of PRIs